## FNAL and UC-UF
| 2001 | [21 empty] | 2002 | [23 empty] | 2003 | [19 empty] | 2004
| J | F | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A | S |  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
Chambers Assembled per Month |  |  |  | 4 |  | 4 |  | 4 |  | 4 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 4 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 4 |  | 6 |  | 6 |  | 6
Chambers Assembled (Cumulative) |  |  |  | 30 | 32 | 34 | 36 | 38 | 40 | 42 | 44 | 47 | 49 | 52 | 54 | 57 | 59 | 62 | 64 | 67 | 69 | 71 | 73 | 76 | 78 | 81 | 83 | 86 | 88 | 91 | 93 | 96 | 98 | 101 | 103 | 106 | 108 | 111 | 113 | 116 | 119 | 121 | 124 | 126 | 129 | 130 | 133 | 136 | 139 | 142 | 145 | 148
Shipments to FAST sites | 2 |  |  |  |  | 10 | [5 empty] | 20 | [5 empty] | 10 |  |  |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  |  | 10 |  | 6
Chambers stored at Fermilab | [5 empty] | 22 | 24 | 26 | 28 | 30 | 33 | 15 | 17 | 20 | 22 | 25 | 26 | 20 | 22 | 25 | 27 | 29 | 21 | 23 | 21 | 19 | 21 | 24 | 16 | 18 | 16 | 14 | 16 | 19 | 11 | 13 | 11 | 9 | 11 | 14 | 7 | 9 | 7 | 4 | 7 | 8 | 1 | 4 | 7 | 0 | 3 | 0
DAQ finalization
FAST site (HV test, then assembly&test) | [6 empty] | 5 | [12 empty] | 5 |  |  | 10
…
10
[19 empty] | 5 | [9 empty] | 15 |  |  | 30
5
5
[30 empty] | 5 | [9 empty] | 15 |  |  | 30
[33 empty] | 5 | [9 empty] | 5 | 10
5
5
[42 empty] | 5 | [9 empty] | 15 |  |  | 30
5
5
[51 empty] | 5 | [8 empty] | 15 |  | 30
[54 empty] | 3 | [7 empty] | 4 | 8
| Delivery of on-chamber boards/cables and mechanics | CFEB | [13 empty] | 50 | 50 | 50 | 150 | 150 | 150 | 150 | 150 | 150 | 200 | 200 | 200 | 200 | 200 | 250 | 250 | 250 | 300 | 300 | 300 | 350 | 350 | 350 | 400 | 400 | 400 | 450 | 450 | 450 | 500 | 500 | 500 | 550 | 550 | 550 | 600 | 600 | 600 | 650 | 650 | 650 | 700 | 700 | 700 | 740
|  | AFEB | [13 empty] | 240 | 240 | 240 | 720 | 720 | 720 | 720 | 720 | 720 | 960 | 960 | 960 | 960 | 960 | 1200 | 1200 | 1200 | 1440 | 1440 | 1440 | 1680 | 1680 | 1680 | 1920 | 1920 | 1920 | 2160 | 2160 | 2160 | 2400 | 2400 | 2400 | 2640 | 2640 | 2640 | 2880 | 2880 | 2880 | 3120 | 3120 | 3120 | 3360 | 3360 | 3360 | 3552
|  | LVDB | [13 empty] | 10 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 60 | 60 | 60 | 70 | 70 | 70 | 80 | 80 | 80 | 90 | 90 | 90 | 100 | 100 | 100 | 110 | 110 | 110 | 120 | 120 | 120 | 130 | 130 | 130 | 140 | 140 | 140 | 148
|  | ALCT-384 | [13 empty] | 10 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 60 | 60 | 60 | 70 | 70 | 70 | 80 | 80 | 80 | 90 | 90 | 90 | 100 | 100 | 100 | 110 | 110 | 110 | 120 | 120 | 120 | 130 | 130 | 130 | 140 | 140 | 140 | 148
|  | Harness-ME23/2 | [13 empty] | 10 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 60 | 60 | 60 | 70 | 70 | 70 | 80 | 80 | 80 | 90 | 90 | 90 | 100 | 100 | 100 | 110 | 110 | 110 | 120 | 120 | 120 | 130 | 130 | 130 | 140 | 140 | 140 | 148
|  | On-ME23/2 mechanics | [13 empty] | 10 | 10 | 10 | 30 | 30 | 30 | 30 | 30 | 30 | 40 | 40 | 40 | 40 | 40 | 50 | 50 | 50 | 60 | 60 | 60 | 70 | 70 | 70 | 80 | 80 | 80 | 90 | 90 | 90 | 100 | 100 | 100 | 110 | 110 | 110 | 120 | 120 | 120 | 130 | 130 | 130 | 140 | 140 | 140 | 148
|  | Large HV Harnesses | [9 empty] | 88 | [12 empty] | 20 | [7 empty] | 20 | [7 empty] | 22
|  | Large HV cables | [9 empty] | 26

## PNPI
2001 | [18 empty] | 2002 | [23 empty] | 2003 | [23 empty] | 2004
J |  | F |  | M | A | M | J |  | J | A | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J | F | M | A | M | J | J | A | S | O | N | D
| Assembled chambers per month | [8 empty] | ME2/1 |  | 2 |  | 4 |  | 4 |  | 4 |  | 4 |  | 5 |  | 5 |  | 5 |  | 5
| Assembled chambers (cumulative) | [10 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 23 | 25 | 28 | 30 | 33 | 35 | 38
| Chambers needed to keep up with FAST site | [10 empty] | 6: 6; 12: 12; 18: 18; 25: 24; 33: 30; 38: 36 |  |  | 38
| FAST site (HV test, then assembly&test) | [10 empty] | 8: 6; 23: 6
| … | [10 empty] | 14: 6; 30: 6
[12 empty] | 20: 6; 38: 6 |  |  |  |  | 20
[12 empty] | 28: 6 |  |  | 6
[12 empty] | 35: 6 |  |  |  |  | 6
[29 empty] | 6 | [6 empty] | 6
[32 empty] | 2 |  |  |  |  | 2 |  |  |  | 18
| On-chamber set deliveries (incremental) | [10 empty] | 8: 6; 14: 6; 20: 6; 28: 6; 35: 6 | 6 |  |  | 2
[12 empty] | 35: ME3/1 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 4 |  | 4
[30 empty] | 5 | 7 | 10 | 12 | 15 | 17 | 20 | 22 | 25 | 27 | 30 | 32 | 34 | 36 | 38
[31 empty] | 4 |  | 10 |  |  | 16 |  | 22 |  |  | 28 |  | 34 |  |  | 38
[32 empty] | 4 | [5 empty] | 4
[34 empty] | 6 | [6 empty] | 6
[37 empty] | 6 | [5 empty] | 6 | [5 empty] | 20
[39 empty] | 6 | [6 empty] | 6
[42 empty] | 6 | [5 empty] | 6
[44 empty] | 6 | [6 empty] | 6
[47 empty] | 4 | [5 empty] | 4 |  |  |  | 18
[32 empty] | 4 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 4
|  |  |  | chamber assembly | [38 empty] | ME4/1 |  |  | 4 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 4
[46 empty] | 4 | 6 | 9 | 11 | 14 | 16 | 19 | 21 | 24 | 26 | 29 | 31 | 34 | 36 | 38
|  |  |  | long term HV test at FAST | [41 empty] | 2 |  |  | 8 |  | 14 |  |  | 20 |  | 26 |  |  | 32 |  | 38
|  |  |  | assembly with electronics and commissioning at FAST | [42 empty] | 2 | [6 empty] | 2
[50 empty] | 6 | [5 empty] | 6
|  |  |  | shipping to CERN | [47 empty] | 6 | [6 empty] | 6
[55 empty] | 6 | [5 empty] | 6 |  |  |  | 20
|  |  |  | arrival to CERN | [52 empty] | 6 | [6 empty] | 6
[60 empty] | 6 | [5 empty] | 6
[62 empty] | 6 | [5 empty] | 6 |  | 18
[47 empty] | 2 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6
| Delivery of on-chamber boards/cables and mechanics |  | CFEB | [11 empty] | 30 | 30 | 30 | 60 | 60 | 60 | 90 | 90 | 90 | 120 | 120 | 120 | 150 | 150 | 180 | 180 | 180 | 210 | 210 | 240 | 240 | 240 | 270 | 270 | 300 | 300 | 300 | 330 | 330 | 360 | 360 | 360 | 390 | 390 | 390 | 420 | 420 | 450 | 450 | 450 | 480 | 480 | 510 | 510 | 510 | 540 | 540 | 570
|  |  | AFEB | [11 empty] | 252 | 252 | 252 | 504 | 504 | 504 | 756 | 756 | 756 | 1008 | 1008 | 1008 | 1260 | 1260 | 1512 | 1512 | 1512 | 1740 | 1740 | 1956 | 1956 | 1956 | 2172 | 2172 | 2388 | 2388 | 2388 | 2604 | 2604 | 2820 | 2820 | 2820 | 3036 | 3036 | 3036 | 3252 | 3252 | 3468 | 3468 | 3468 | 3684 | 3684 | 3900 | 3900 | 3900 | 4116 | 4116 | 4332
|  |  | LVDB | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 36 | 36 | 36 | 42 | 42 | 48 | 48 | 48 | 54 | 54 | 60 | 60 | 60 | 66 | 66 | 72 | 72 | 72 | 78 | 78 | 78 | 84 | 84 | 90 | 90 | 90 | 96 | 96 | 102 | 102 | 102 | 108 | 108 | 114
|  |  | ALCT-672 | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 36 | 36 | 36 | 42 | 42 | 48 | 48 | 48 | 54 | 54 | 60 | 60 | 60 | 66 | 66 | 72 | 72 | 72 | 78 | 78 | 78 | 84 | 84 | 90 | 90 | 90 | 96 | 96 | 102 | 102 | 102 | 108 | 108 | 114
|  |  | Harness-ME2/1 | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 36 | 36 | 36 | 38
|  |  | Harness-ME3/1 | [28 empty] | 4 | 4 | 10 | 10 | 10 | 16 | 16 | 22 | 22 | 22 | 28 | 28 | 34 | 34 | 34 | 38
|  |  | Harness-ME4/1 | [43 empty] | 2 | 2 | 2 | 8 | 8 | 14 | 14 | 14 | 20 | 20 | 26 | 26 | 26 | 32 | 32 | 38
|  |  | On-ME2/1 mechanics | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 24 | 30 | 30 | 36 | 36 | 36 | 38
|  |  | On-ME3/1 mechanics | [28 empty] | 4 | 4 | 10 | 10 | 10 | 16 | 16 | 22 | 22 | 22 | 28 | 28 | 34 | 34 | 34 | 38
|  |  | On-ME4/1 mechanics | [43 empty] | 2 | 2 | 2 | 8 | 8 | 14 | 14 | 14 | 20 | 20 | 26 | 26 | 26 | 32 | 32 | 38
|  |  | Small HV hatnesses |  |  |  |  | 23 |  |  |  | 14: 20; 33: 20 | [5 empty] | 17 | [7 empty] | 20 | [7 empty] | 14
|  |  | Small HV cables | [7 empty] | 15

## IHEP
2001 | [18 empty] | 2002 | [23 empty] | 2003 | [23 empty] | 2004
J |  | F |  | M | A | M | J |  | J | A | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J |  | J |  | A |  | S |  | O |  | N |  | D |  | J |  | F |  | M |  | A |  | M |  | J | J |  | A | S | O | N | D
| Assembled chambers per month | [8 empty] | ME1/2 |  | 2 |  | 4 |  | 4 |  | 4 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5 |  | 5
| Assembled chambers (cumulative) | [12 empty] | 6 | 8 | 10 | 12 | 14 | 16 | 19 | 20 | 24 | 25 | 29 | 30 | 34 | 35 | 39 | 41 | 44 | 46 | 49 | 51 | 54 | 56 | 59 | 61 | 64 | 66 | 69 | 71 | 74
| Chambers needed to keep up with FAST site | [12 empty] | 6 |  |  | 12 |  |  | 18 |  |  | 24 |  | 30 |  |  | 36 |  | 42 |  |  | 48 |  | 54 |  |  | 60 |  | 66 |  |  | 72 |  | 74
| FAST site (HV test, then assembly&test) | [13 empty] | 6 | [6 empty] | 6
| … | [16 empty] | 6 | [6 empty] | 6
[21 empty] | 6 | [6 empty] | 6 |  |  |  | 18
[24 empty] | 6 | [5 empty] | 6
[26 empty] | 6 | [6 empty] | 6
[29 empty] | 6 | [5 empty] | 6 |  |  |  | 18
[31 empty] | 6 | [6 empty] | 6
[34 empty] | 6 | [5 empty] | 6
[36 empty] | 6 | [6 empty] | 6 |  |  |  | 18
[39 empty] | 6 | [5 empty] | 6
[41 empty] | 6 | [6 empty] | 6
[44 empty] | 6 | [5 empty] | 6
[46 empty] | 2 |  |  |  |  | 2
[15 empty] | 6 |  |  | 6 |  |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 6 |  |  | 6 |  | 2
[24 empty] | Assembled chambers per month | [15 empty] | ME1/3 |  |  |  | 4 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 4
[24 empty] | Assembled chambers (cumulative) | [18 empty] | 2 | 4 | 6 | 10 | 12 | 16 | 18 | 22 | 24 | 28 | 30 | 34 | 36 | 40 | 42 | 46 | 48 | 52 | 54 | 58 | 60 | 64 | 66 | 70 | 72 | 74
[24 empty] | Chambers needed to keep up with FAST site | [20 empty] | 4 |  |  | 10 |  | 16 |  | 22 |  | 28 |  | 34 |  | 40 |  | 46 |  | 52 |  | 58 |  | 64 |  | 70 |  | 74
[24 empty] | FAST site (HV test, then assembly&test) | [21 empty] | 4 | [5 empty] | 4 |  |  |  | 18
[24 empty] | … | [24 empty] | 6 |  |  |  |  | 6
|  |  |  | chamber assembly | [46 empty] | 6 |  |  |  |  | 6
[53 empty] | 6 |  |  |  |  | 6 |  |  |  | 18
|  |  |  | long term HV test at FAST | [50 empty] | 6 |  |  |  |  | 6
[57 empty] | 6 |  |  |  |  | 6
|  |  |  | assembly with electronics and commissioning at FAST | [54 empty] | 6 |  |  |  |  | 6 |  |  |  | 18
[61 empty] | 6 |  |  |  |  | 6
|  |  |  | shipping to CERN | [58 empty] | 6 |  |  |  |  | 6
[65 empty] | 6 |  |  |  |  | 6 |  |  |  | 18
|  |  |  | arrival to CERN | [62 empty] | 6 |  |  |  |  | 6
[69 empty] | 6 |  |  |  |  | 6
[71 empty] | 4 |  |  |  |  | 4 |  |  | 16
[46 empty] | 4 |  |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 6 |  | 4
| Delivery of on-chamber boards/cables and mechanics |  | CFEB | [11 empty] | 30 | 30 | 30 | 60 | 60 | 60 | 90 | 90 | 90 | 120 | 120 | 150 | 150 | 150 | 180 | 180 | 210 | 210 | 210 | 240 | 240 | 270 | 270 | 270 | 300 | 300 | 330 | 330 | 330 | 360 | 360 | 386 | 386 | 386 | 410 | 410 | 434 | 434 | 458 | 458 | 482 | 482 | 506 | 506 | 530 | 530 | 554 | 554 | 578 | 578 | 602 | 602 | 626 | 626 | 650 | 650 | 666
|  |  | AFEB | [11 empty] | 144 | 144 | 144 | 288 | 288 | 288 | 432 | 432 | 432 | 576 | 576 | 720 | 720 | 720 | 864 | 864 | 1008 | 1008 | 1008 | 1152 | 1152 | 1296 | 1296 | 1296 | 1440 | 1440 | 1584 | 1584 | 1584 | 1728 | 1728 | 1824 | 1824 | 1824 | 1896 | 1896 | 1968 | 1968 | 2040 | 2040 | 2112 | 2112 | 2184 | 2184 | 2256 | 2256 | 2328 | 2328 | 2400 | 2400 | 2472 | 2472 | 2544 | 2544 | 2616 | 2616 | 2664
|  |  | LVDB | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 42 | 42 | 42 | 48 | 48 | 54 | 54 | 54 | 60 | 60 | 66 | 66 | 66 | 72 | 72 | 78 | 78 | 78 | 84 | 84 | 90 | 90 | 96 | 96 | 102 | 102 | 108 | 108 | 114 | 114 | 120 | 120 | 126 | 126 | 132 | 132 | 138 | 138 | 144 | 144 | 148
|  |  | ALCT-384 | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 42 | 42 | 42 | 48 | 48 | 54 | 54 | 54 | 60 | 60 | 66 | 66 | 66 | 72 | 72 | 74
|  |  | ALCT-288 | [42 empty] | 4 | 4 | 4 | 10 | 10 | 16 | 16 | 22 | 22 | 28 | 28 | 34 | 34 | 40 | 40 | 46 | 46 | 52 | 52 | 58 | 58 | 64 | 64 | 70 | 70 | 74
|  |  | Harness-ME1/2 | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 42 | 42 | 42 | 48 | 48 | 54 | 54 | 54 | 60 | 60 | 66 | 66 | 66 | 72 | 72 | 74
|  |  | Harness-ME1/3 | [42 empty] | 4 | 4 | 4 | 10 | 10 | 16 | 16 | 22 | 22 | 28 | 28 | 34 | 34 | 40 | 40 | 46 | 46 | 52 | 52 | 58 | 58 | 64 | 64 | 70 | 70 | 74
|  |  | On-ME1/2 mechanics | [11 empty] | 6 | 6 | 6 | 12 | 12 | 12 | 18 | 18 | 18 | 24 | 24 | 30 | 30 | 30 | 36 | 36 | 42 | 42 | 42 | 48 | 48 | 54 | 54 | 54 | 60 | 60 | 66 | 66 | 66 | 72 | 72 | 74
|  |  | On-ME1/3 mechanics | [42 empty] | 4 | 4 | 4 | 10 | 10 | 16 | 16 | 22 | 22 | 28 | 28 | 34 | 34 | 40 | 40 | 46 | 46 | 52 | 52 | 58 | 58 | 64 | 64 | 70 | 70 | 74
|  |  | Small harnesses |  |  |  |  | 24 | [9 empty] | 20 | [7 empty] | 20 | [7 empty] | 20 | [7 empty] | 24 | [7 empty] | 24 | [7 empty] | 16
|  |  | Small cables | [7 empty] | 15

## Flow of on-CSC parts
Last time updated: July 24, 2001
|  | UC and UF |  | PNPI |  |  | IHEP |  | Cumulative Board Production Needs
Year | Month | ME23/2 sets shipped to UC | ME23/2 sets shipped to UF | ME2/1 sets shipped to PNPI | ME3/1 sets shipped to PNPI | ME4/1 sets shipped to PNPI | ME1/2 sets shipped to IHEP | ME1/3 sets shipped to IHEP | CFEB needs | AFEB needs | ALCT-384 needs | ALCT-672 needs | ALCT-288 needs | LVDB needs
2001 | J
A
| S | 5 | 5 | [5 empty] | 50 | 240 | 10 |  |  | 10
[9 empty] | 50 | 240 | 10 |  |  | 10
| O | [7 empty] | 50 | 240 | 10 |  |  | 10
|  | 10 | 10 | [5 empty] | 150 | 720 | 30 |  |  | 30
| N |  |  | 12 |  |  | 12 |  | 270 | 1512 | 42 | 6 |  | 54
[9 empty] | 270 | 1512 | 42 | 6 |  | 54
| D | [7 empty] | 270 | 1512 | 42 | 6 |  | 54
[9 empty] | 270 | 1512 | 42 | 12 |  | 54
2002 | J | [7 empty] | 270 | 1512 | 42 | 12 |  | 54
|  | 10 | 10 | [5 empty] | 370 | 1992 | 62 | 12 |  | 74
| F |  |  | 12 |  |  | 12 |  | 490 | 2784 | 74 | 24 |  | 98
[9 empty] | 490 | 2784 | 74 | 24 |  | 98
| M | [7 empty] | 490 | 2784 | 74 | 24 |  | 98
[9 empty] | 490 | 2784 | 74 | 24 |  | 98
| A | [7 empty] | 490 | 2784 | 74 | 24 |  | 98
|  |  |  | 14 |  |  | 12 |  | 620 | 3660 | 86 | 38 |  | 124
| M | [7 empty] | 620 | 3660 | 86 | 38 |  | 124
|  | 10 | 10 | [5 empty] | 720 | 4140 | 106 | 38 |  | 144
| J | [7 empty] | 720 | 4140 | 106 | 38 |  | 144
[9 empty] | 720 | 4140 | 106 | 38 |  | 144
| J |  |  |  | 12 |  | 12 |  | 840 | 4860 | 118 | 50 |  | 168
[9 empty] | 840 | 4860 | 118 | 50 |  | 168
| A | [7 empty] | 840 | 4860 | 118 | 50 |  | 168
|  | 10 | 10 | [5 empty] | 940 | 5340 | 138 | 50 |  | 188
| S | [7 empty] | 940 | 5340 | 138 | 50 |  | 188
[5 empty] | 12 |  | 12 |  | 1060 | 6060 | 150 | 62 |  | 212
| O | [7 empty] | 1060 | 6060 | 150 | 62 |  | 212
[9 empty] | 1060 | 6060 | 150 | 62 |  | 212
| N | [7 empty] | 1060 | 6060 | 150 | 62 |  | 212
|  | 10 | 10 | [5 empty] | 1160 | 6540 | 170 | 62 |  | 232
| D |  |  |  | 14 |  | 14 |  | 1300 | 7380 | 184 | 76 |  | 260
[9 empty] | 1300 | 7380 | 184 | 76 |  | 260
2003 | J | [7 empty] | 1300 | 7380 | 184 | 76 |  | 260
[9 empty] | 1300 | 7380 | 184 | 76 |  | 260
| F | [7 empty] | 1300 | 7380 | 184 | 76 |  | 260
|  | 10 | 10 |  |  | 12 |  | 12 | 1508 | 8436 | 204 | 88 | 12 | 304
| M | [7 empty] | 1508 | 8436 | 204 | 88 | 12 | 304
[9 empty] | 1508 | 8436 | 204 | 88 | 12 | 304
| A | [7 empty] | 1508 | 8436 | 204 | 88 | 12 | 304
[9 empty] | 1508 | 8436 | 204 | 88 | 12 | 304
| M |  |  |  |  | 12 |  | 12 | 1616 | 9012 | 204 | 100 | 24 | 328
|  | 9 | 9 | [5 empty] | 1706 | 9444 | 222 | 100 | 24 | 346
| J | [7 empty] | 1706 | 9444 | 222 | 100 | 24 | 346
[9 empty] | 1706 | 9444 |  | 100 | 24 | 346
| J |  |  |  |  | 14 |  | 12 | 1824 | 10092 |  | 114 | 36 | 372
[9 empty] | 1824 | 10092 |  |  | 36 | 372
| A | [7 empty] | 1824 | 10092 |  |  | 36 | 372
[9 empty] | 1824 | 10092 |  |  | 36 | 372
| S | [6 empty] | 12 | 1872 | 10236 |  |  | 48 | 384
[9 empty] | 1872 | 10236 |  |  | 48 | 384
| O | [7 empty] | 1872 | 10236 |  |  | 48 | 384
[9 empty] | 1872 | 10236 |  |  | 48 | 384
| N | [6 empty] | 12 | 1920 | 10380 |  |  | 60 | 396
[9 empty] | 1920 | 10380 |  |  | 60 | 396
| D | [7 empty] | 1920 | 10380 |  |  | 60 | 396
[9 empty] | 1920 | 10380 |  |  | 60 | 396
2004 | J | [6 empty] | 14 | 1976 | 10548 |  |  | 74 | 410
TOTAL |  | 74 | 74 | 38 | 38 | 38 | 74 | 74
- | Each shipment consists of 7 boxes
- | Each box should have full qty of boards, cables, parts for the number of chambers shown in the table
- | Boxes for US FAST sites are shipped directly to UC and UF
- | Boxes for PNPI and IHEP FAST sites are shipped to Fermilab and
Fermilab without unpacking them redirects a kit of 7 boxes to PNPI and IHEP
| Box No. |  |  |  |  | Content | [6 empty] | Provided by
| 1 |  | CFEBs, CFEB-CSC cables, CFEB-CFEB cables | [9 empty] | OSU
| 2 |  | AFEBs assembled, AFEB-CSC cables for ME1/2 & ME1/3 | [9 empty] | CMU
| 3 |  | LVDBs, LVDB-CFEB cables, LVDB-ALCT cables | [9 empty] | Wisconsin
| 4 |  | ALCTs, ALCT-CSC cables | [9 empty] | UCLA
| 5 |  | ALCT-AFEB cables (or harnesses for ME23/2) | [9 empty] | CMU
| 6 |  | Cooling Plate | [9 empty] | Fermilab
| 7 |  | On-chamber hardware | [9 empty] | Wisconsin
Note on E12: No ALCTs
Note on C11: Only 7 sets of CFEBs
Note on D11: Only 7 sets of CFEBs
Note on C17: 13 sets of CFEBs (to catch up with previous lack)
Note on D17: 13 sets of CFEBs (to catch up with previous lack)
Note on H12: No ALCTs